## Risk Cube
Tasks |  | !Likelihood | Impact
1 | Get BMS IC working | 3 | 5
2 | Convert battery voltage into 12V and 24V | 2 | 4
3 | Display data | 1 | 2
4 | Log data as .csv to sd card | 3 | 1
5 | Have user initiate data logging | 1 | 1
6 | Be able to charge battery pack using wall adapter | 1 | 2
7 | Layout PCB | 2 | 3
5
4
| 3 | 4 |  |  |  | 1
| 2 |  |  | 7 | 2
| 1 | 5 | 3,6
|  | 1 | 2 | 3 | 4 | 5
Likelihood
Impact